## projects_vmitchell@tiaonline.or
Project | Project_State | Project_Type | Project_Percent_Complete | Notes | Scheduled_Finish | Scheduled_Start | Actual_Finish | Last_Updated | Last_Contributed | Project_Contact | Resource_Names | Num_Contributions | Active?
ISO/IEC 10192-4-3 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  |  |  | 2021-06-22 | 2021-06-23 | Teesha Jenkins | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 3 | 1
IEC 62150-6 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  |  |  | 2021-07-06 | 2021-11-01 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 9 | 1
PNW 86C-1729 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  |  |  | 2021-07-06 | 2021-07-09 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 2 | 1
PNW 86C-1730 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  |  |  | 2021-07-06 | 2021-07-09 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 3 | 1
IEC 61753-091-02 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  |  |  | 2021-07-12 | 2022-01-11 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 8 | 1
IEC 61753-051-02 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  |  |  | 2021-08-02 | 2022-05-02 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 15 | 1
IEC TR 60825-3 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  |  |  | 2021-10-26 | 2021-10-26 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 6 | 1
IEC 62664-1-10 ED1 | Preliminary (PWI-10%) | IEC TAG Project | 0 |  |  |  |  | 2022-01-10 | 2022-01-11 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 1 | 1
IEC 63267-2-1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2010-05-21 |  | 2022-06-27 | 2022-07-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 3 | 1
IEC TR 62471-4 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2011-04-08 |  | 2022-05-23 | 2022-05-23 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 0 | 1
455-178-C (TIA Adopted) | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2013-09-16 | 2021-04-14 | 2022-01-10 | 2021-03-01 | Cheryl Thibideau | TR-42.12 Optical Fibers and Cables | 18 | 1
1152-A (Reaffirmation) | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2013-11-04 | 2021-07-16 | 2022-08-24 | 2021-07-15 | Cheryl Thibideau | TR-42.7 Telecommunications Copper Cabling Systems | 9 | 1
5021 | PublAnnouncePosted (100%) | TIA-Only | 100 |  |  | 2015-02-09 | 2021-04-13 | 2021-04-28 | 2021-03-22 | Cheryl Thibideau | TR-42.7 Telecommunications Copper Cabling Systems | 2 | 1
IEC 60825-4 ED3 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-08-31 | 2015-08-07 |  | 2022-05-09 | 2022-07-12 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 9 | 1
IEC TR 61156-1-3/AMD1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-06-30 | 2016-01-22 |  | 2021-08-30 | 2022-05-17 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 9 | 1
IEC 61935-2 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2016-02-19 |  | 2021-11-15 | 2021-11-15 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 11 | 1
IEC 61300-3-7 ED3 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2021-10-31 | 2016-04-29 |  | 2021-06-08 | 2021-06-09 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 13 | 1
IEC 61757-2-1 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2021-09-30 | 2016-07-01 |  | 2021-06-08 | 2021-07-27 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 15 | 1
IEC 61755-2-2 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-01-31 | 2016-09-30 |  | 2021-12-07 | 2022-09-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 17 | 1
IEC 61755-2-1 ED2 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-10-31 | 2016-09-30 |  | 2022-07-06 | 2022-08-22 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 16 | 1
IEC 61757-1-2 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-08-31 | 2016-10-12 |  | 2022-06-27 | 2022-06-27 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 8 | 1
IEC 61754-6 ED3 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-04-30 | 2016-10-14 |  | 2021-12-13 | 2022-01-31 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 3 | 1
IEC 61754-4 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2016-10-14 |  | 2021-12-14 | 2022-01-31 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 3 | 1
IEC 62471-6 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2016-12-06 |  | 2022-05-02 | 2022-09-27 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 4 | 1
IEC 61754-7-4 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-06-30 | 2016-12-07 |  | 2021-06-21 | 2021-06-21 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 8 | 1
4957.210-B | PublAnnouncePosted (100%) | ANSI Project | 100 | Project request form exists in the old Standards tools system - submitted August 2017. | 2021-10-15 | 2017-04-08 | 2021-09-28 | 2021-09-29 | 2021-09-16 | Teesha Jenkins | TR-51 Smart Utility Networks | 17 | 1
IEC 61280-4-3 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-01-31 | 2017-05-17 |  | 2021-12-07 | 2022-03-21 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 13 | 1
IEC 60794-1-219 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-03-31 | 2017-07-17 |  | 2021-05-27 | 2021-11-15 | Florence Otieno | IEC SC86A Fibres & Cables | 15 | 1
IEC 62496-2-61 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-08-31 | 2017-08-23 |  | 2021-06-07 | 2021-10-25 | Florence Otieno | IEC TC86 Fibre Optics | 8 | 1
IEC 62496-2-5 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2017-08-23 |  | 2022-01-10 | 2022-09-26 | Florence Otieno | IEC TC86 Fibre Optics | 5 | 1
IEC 61300-2-6 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-07-31 | 2017-09-05 |  | 2022-06-13 | 2022-09-13 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 12 | 1
568.5 | PublAnnouncePosted (100%) | ANSI Project | 100 | Project created using the project request form submitted on 9/25/2017 in the old system. |  | 2017-09-25 | 2022-03-07 | 2022-03-17 | 2022-09-08 | Cheryl Thibideau | TR-42.7 Telecommunications Copper Cabling Systems | 25 | 1
604-19 | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2017-11-02 | 2021-09-09 | 2021-10-04 | 2022-08-01 | Cheryl Thibideau | TR-42.13 Passive Optical Devices and Fiber Optic Metrology | 12 | 1
IEC 61156-13 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2017-11-20 |  | 2022-04-04 | 2022-04-04 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 15 | 1
IEC SRD 63188 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-08-31 | 2017-11-24 |  | 2021-09-29 | 2022-04-19 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 17 | 1
IEC 62037-8 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-09-30 | 2017-12-06 |  | 2021-09-07 | 2022-08-15 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 9 | 1
IEC 61169-67 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-05-31 | 2017-12-21 |  | 2021-08-09 | 2022-02-07 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 10 | 1
102.CCAA-C | Committee Ballot (40%) | TIA-Only | 40 | This document was originally published as an ANSI document (ANSI/TIA-102.CCAA-B). This revision will be published as a TIA-only standard. Approved by the P25 SC. The P25 logo will be applied to the standard. |  | 2018-02-07 |  | 2022-07-26 | 2022-04-01 | Teesha Jenkins | TR-8.1 Equipment Measurement Procedures | 12 | 1
102.CAAA-F | PublAnnouncePosted (100%) | TIA-Only | 100 | Project being created (back-filled) in preparation of reballot. This standard was previously an ANSI but has been re-designated as a TIA-only. Motion to publish recorded via general ballot. | 2021-06-30 | 2018-03-01 | 2021-09-14 | 2021-11-08 | 2021-09-13 | Victoria Mitchell | TR-8.1 Equipment Measurement Procedures | 14 | 1
102.CAAB-E | PublAnnouncePosted (100%) | TIA-Only | 100 |  | 2021-06-30 | 2018-03-01 | 2021-09-15 | 2021-11-08 | 2021-09-13 | Victoria Mitchell | TR-8.1 Equipment Measurement Procedures | 10 | 1
603-F | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2018-03-01 |  | 2021-04-26 | 2021-04-26 | Teesha Jenkins | TR-8.1 Equipment Measurement Procedures | 6 | 1
102.CCAB-B | Re-Ballot_Default (60%) | TIA-Only | 60 | The previous revision was an ANSI/TIA standard (ANSI/TIA-102.CCAB-A). This revision will be developed and published as a TIA-only standard. Approved by the P25 SC. The P25 logo will be applied to the standard. |  | 2018-03-01 |  | 2022-07-26 | 2022-06-10 | Teesha Jenkins | TR-8.1 Equipment Measurement Procedures | 19 | 1
IEC 61169-54 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2018-06-15 |  | 2021-08-16 | 2021-08-16 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 1 | 1
IEC SRD 63233-1 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-10-31 | 2018-07-20 |  | 2021-11-01 | 2022-03-14 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 15 | 1
IEC 60966-2-8 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-04-30 | 2018-07-27 |  | 2021-09-07 | 2022-06-06 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 9 | 1
IEC 60966-4-3 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-06-30 | 2018-07-27 |  | 2021-11-01 | 2022-06-06 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 8 | 1
IEC 60966-4-2 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2018-07-27 |  | 2022-04-11 | 2022-06-06 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 10 | 1
IEC 60050-831 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-02-28 | 2018-08-03 |  | 2022-01-24 | 2022-01-24 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 15 | 1
IEC 62037-7 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-12-31 | 2018-09-04 |  | 2022-08-22 | 2022-08-22 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 9 | 1
IEC 62783-1-1 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2018-10-10 |  | 2021-07-27 | 2022-01-24 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 9 | 1
4966-A | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2018-10-12 | 2022-02-03 | 2022-08-16 | 2022-03-01 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 15 | 1
IEC 62153-4-15 ED2 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2021-08-31 | 2018-10-26 |  | 2021-07-12 | 2021-07-12 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
ISO/IEC 15045-3-1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-03-31 | 2018-11-13 |  | 2022-03-14 | 2022-03-14 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 8 | 1
IEC 60794-1-3-40-ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2018-12-01 |  | 2022-02-22 | 2022-04-11 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC 60794-3-40 ED2 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-08-31 | 2018-12-10 |  | 2022-01-10 | 2022-02-22 | Florence Otieno | IEC SC86A Fibres & Cables | 5 | 1
IEC 61755-3-2 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-11-30 | 2019-01-08 |  | 2021-12-06 | 2022-03-14 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 13 | 1
IEC 61755-3-1 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2019-01-08 |  | 2021-12-06 | 2022-03-14 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 14 | 1
IEC TS 60825-19 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-04-30 | 2019-01-14 |  | 2022-04-04 | 2022-07-25 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 9 | 1
IEC 61169-68 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2019-01-24 |  | 2021-08-16 | 2022-02-07 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 3 | 1
IEC 61169-1-5 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2019-01-24 |  | 2021-08-16 | 2022-01-24 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 4 | 1
804-D | PublAnnouncePosted (100%) | TIA-Only | 100 |  | 2021-08-31 | 2019-02-06 | 2021-10-12 | 2021-10-13 | 2021-09-27 | Teesha Jenkins | TR-8 Mobile and Personal Private Radio Standards, TR-8.11 Antenna Systems | 4 | 1
ISO/IEC 14763-3 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2019-02-18 |  | 2022-05-09 | 2022-08-08 | Teesha Jenkins | USNC TAG SC25/WG 3 to ISO/IEC JTC1/SC25/WG3 Customer Premises Cabling | 13 | 1
ISO/IEC 24383 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-10-31 | 2019-02-18 |  | 2021-11-08 | 2022-08-16 | Florence Otieno | USNC TAG SC25/WG 3 to ISO/IEC JTC1/SC25/WG3 Customer Premises Cabling | 21 | 1
IEC 61753-085-02 ED1 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2021-08-30 | 2019-04-04 |  | 2021-07-06 | 2021-07-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
ISO/IEC 15045-3-2 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2019-05-01 |  | 2022-03-07 | 2022-03-14 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 9 | 1
IEC 62807-3 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-04-30 | 2019-06-06 |  | 2022-04-11 | 2022-04-11 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 11 | 1
455-3-C | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2019-06-11 |  | 2021-05-14 | 2021-05-14 | Cheryl Thibideau | TR-42.12 Optical Fibers and Cables | 11 | 1
IEC 62807-3-10 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-04-30 | 2019-06-13 |  | 2022-04-11 | 2022-04-11 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 11 | 1
IEC 60825-12 ED3 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2023-01-31 | 2019-06-28 |  | 2022-09-26 | 2022-09-26 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 12 | 1
IEC 60794-1-401 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2019-07-01 |  | 2021-06-01 | 2021-06-21 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC SRD 63273 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2019-07-03 |  | 2021-09-27 | 2021-09-29 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 6 | 1
IEC SRD 63273-1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2019-07-03 |  | 2022-08-01 | 2022-08-01 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 2 | 1
IEC 63295 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-08-31 | 2019-07-09 |  | 2021-11-15 | 2022-02-07 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 9 | 1
IEC 61169-1-6 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-04-30 | 2019-07-11 |  | 2022-01-10 | 2022-02-07 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 10 | 1
IEC 63138-3 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  |  | 2019-07-11 |  | 2021-11-15 | 2022-02-14 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 10 | 1
IEC TR 60825-14 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2019-07-16 |  | 2021-10-26 | 2021-10-26 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 6 | 1
IEC 61169-69 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-09-30 | 2019-07-29 |  | 2021-09-07 | 2022-06-01 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 7 | 1
IEC 61169-71 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-07-31 | 2019-07-29 |  | 2022-03-28 | 2022-05-17 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 9 | 1
IEC 62153-4-16 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2019-08-15 |  | 2021-07-26 | 2021-07-26 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 6 | 1
IEC SRD 63152-2 ED1 | Preliminary (PWI-10%) | IEC TAG Project | 0 |  | 2023-08-31 | 2019-08-20 |  | 2021-11-29 | 2022-09-07 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 6 | 1
IEC 62153-4-5 ED2 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2021-09-30 | 2019-08-23 |  | 2021-08-09 | 2021-08-09 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 6 | 1
5071 | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2019-09-24 | 2022-06-28 | 2022-08-16 | 2022-06-16 | Teesha Jenkins | TR-42.7 Telecommunications Copper Cabling Systems | 29 | 1
102.BACA-B-3 | PublAnnouncePosted (100%) | TIA-Only | 100 | Addendum 3 to 102.BACA-A |  | 2019-10-14 | 2021-04-14 | 2021-04-26 | 2021-02-23 | Teesha Jenkins | TR-8.19 Wireline System Interfaces | 16 | 1
102.AABC-E-1 | Proj Form Initiated (20%) | ANSI Project | 20 | This is an update to the existing project 102.AABC-E |  | 2019-10-17 |  | 2019-10-17 | 2019-10-17 | Teesha Jenkins | TR-8.10 Trunking and Conventional Control | 1 | 1
ISO/IEC 14763-5 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-05-31 | 2019-10-31 |  | 2022-04-25 | 2022-08-04 | Florence Otieno | USNC TAG SC25/WG 3 to ISO/IEC JTC1/SC25/WG3 Customer Premises Cabling | 5 | 1
ISO/IEC 11801-1/AMD1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-11-30 | 2019-11-01 |  | 2021-11-08 | 2022-08-16 | Florence Otieno | USNC TAG SC25/WG 3 to ISO/IEC JTC1/SC25/WG3 Customer Premises Cabling | 19 | 1
1005-B | Committee Ballot (30%) | ANSI Project | 30 |  |  | 2019-11-05 |  | 2020-12-10 | 2020-12-10 | Cheryl Thibideau | TR-42.9 Industrial Telecommunications Infrastructure | 6 | 1
IEC 61754-36 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-02-28 | 2019-11-07 |  | 2022-01-05 | 2022-04-04 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 13 | 1
IEC 61753-043-02 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-10-31 | 2019-11-25 |  | 2022-07-06 | 2022-08-22 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 9 | 1
IEC 61754-37 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-01-31 | 2019-11-26 |  | 2022-01-25 | 2022-04-26 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
IEC 62037-1 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2019-12-20 |  | 2021-09-13 | 2021-11-08 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 3 | 1
IEC 62037-3 ED2 | Approval (FDIC-90%) | IEC TAG Project | 0 |  | 2021-12-31 | 2019-12-26 |  | 2021-09-13 | 2021-11-01 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 6 | 1
IEC 62037-5 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2019-12-26 |  | 2021-09-13 | 2021-11-01 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 3 | 1
526-14-D | Re-Ballot_Default (60%) | ANSI Project | 60 |  |  | 2020-01-08 |  | 2021-12-10 | 2022-08-05 | Teesha Jenkins | TR-42.11 Optical Systems | 22 | 1
568.3-E | Re-Ballot_Default (60%) | ANSI Project | 60 |  |  | 2020-01-09 |  | 2021-04-09 | 2022-04-12 | Cheryl Thibideau | TR-42.11 Optical Systems | 29 | 1
IEC 61156-1 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-10-31 | 2020-01-16 |  | 2021-08-03 | 2022-05-17 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 7 | 1
IEC TR 61156-1-2 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-11-30 | 2020-01-17 |  | 2022-01-18 | 2022-01-18 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 5 | 1
102.CABC-C-1 | PublAnnouncePosted (100%) | TIA-Only | 100 |  |  | 2020-02-13 | 2022-05-10 | 2022-08-16 | 2022-05-04 | Teesha Jenkins | TR-8.25 Compliance Assessment | 7 | 1
88.3-F | PublAnnouncePosted (100%) | TIA-Only | 100 |  |  | 2020-02-13 | 2022-03-15 | 2022-03-17 | 2022-03-17 | Teesha Jenkins | TR-8.18 Wireless Systems Compatibility - Interference and Coverage | 10 | 1
88.2-F | PublAnnouncePosted (100%) | TIA-Only | 100 |  |  | 2020-02-13 | 2021-04-12 | 2021-04-26 | 2021-04-12 | Teesha Jenkins | TR-8.18 Wireless Systems Compatibility - Interference and Coverage | 18 | 1
IEC 61753-022-13 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2020-02-21 |  | 2021-06-14 | 2021-06-15 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 5 | 1
IEC 61753-022-07 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2020-02-21 |  | 2021-06-14 | 2021-06-15 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 5 | 1
IEC 61196-1-326 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-11-30 | 2020-02-26 |  | 2022-08-08 | 2022-09-27 | Florence Otieno | IEC SC46A Coaxial Cables | 10 | 1
604-10-C | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2020-02-28 | 2021-08-18 | 2021-10-04 | 2022-03-25 | Cheryl Thibideau | TR-42.13 Passive Optical Devices and Fiber Optic Metrology | 15 | 1
ISO/IEC 15067-3-31 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2020-03-12 |  | 2021-11-01 | 2022-07-25 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 10 | 1
IEC SRD 63233-2 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-08-31 | 2020-03-27 |  | 2022-09-14 | 2022-09-14 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 9 | 1
IEC TR 63309 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2020-04-01 |  | 2021-06-01 | 2022-09-13 | Florence Otieno | IEC SC86A Fibres & Cables | 4 | 1
ISO/IEC-11801-6/AMD1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-12-31 | 2020-04-01 |  | 2021-10-12 | 2022-09-20 | Florence Otieno | USNC TAG SC25/WG 3 to ISO/IEC JTC1/SC25/WG3 Customer Premises Cabling | 16 | 1
IEC 60794-1-220 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-07-31 | 2020-04-16 |  | 2022-01-04 | 2022-02-23 | Florence Otieno | IEC SC86A Fibres & Cables | 10 | 1
568.7 | Re-Ballot_Default (60%) | ANSI Project | 60 |  |  | 2020-04-22 |  | 2022-06-02 | 2022-08-31 | Teesha Jenkins | TR-42.9 Industrial Telecommunications Infrastructure | 17 | 1
IEC 61753-111-07 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  |  | 2020-05-01 |  | 2021-07-15 | 2021-08-30 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 6 | 1
IEC 61753-111-09 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  |  | 2020-05-01 |  | 2021-07-15 | 2021-08-30 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 6 | 1
IEC TS 63334 ED1 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2022-01-31 | 2020-05-01 |  | 2021-08-30 | 2021-10-13 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 8 | 1
IEC 61196-7 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2020-05-15 |  | 2021-08-16 | 2021-08-16 | Florence Otieno | IEC SC46A Coaxial Cables | 1 | 1
IEC 60794-1-31 ED2 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2021-09-30 | 2020-05-29 |  | 2021-05-27 | 2021-05-27 | Florence Otieno | IEC SC86A Fibres & Cables | 7 | 1
IEC 60794-3 ED5 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-03-31 | 2020-06-01 |  | 2021-12-07 | 2022-01-31 | Florence Otieno | IEC SC86A Fibres & Cables | 8 | 1
IEC 61753-101-03-ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2021-11-30 | 2020-06-01 |  | 2021-08-09 | 2021-09-08 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 7 | 1
IEC 61753-131-03 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-04-30 | 2020-06-10 |  | 2021-06-21 | 2021-09-13 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 9 | 1
IEC 61196-6 ED2 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2021-09-30 | 2020-06-10 |  | 2021-08-16 | 2021-08-16 | Florence Otieno | IEC SC46A Coaxial Cables | 7 | 1
IEC 61753-081-06 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-09-30 | 2020-06-11 |  | 2022-08-16 | 2022-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 15 | 1
IEC 61753-081-03 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2020-06-11 |  | 2022-08-15 | 2022-08-15 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 13 | 1
IEC 61196-6-1 ED2 | Publication (APUB-95%) | IEC TAG Project | 95 |  | 2021-09-30 | 2020-06-16 |  | 2021-08-16 | 2021-08-16 | Florence Otieno | IEC SC46A Coaxial Cables | 7 | 1
IEC TS 60825-20 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-12-31 | 2020-06-18 |  | 2021-08-30 | 2022-04-04 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 5 | 1
IEC 62496-4-3 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-09-30 | 2020-07-10 |  | 2021-08-02 | 2022-06-01 | Florence Otieno | IEC TC86 Fibre Optics | 7 | 1
IEC 61156-15 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-07-31 | 2020-07-13 |  | 2021-08-16 | 2022-05-10 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 7 | 1
IEC 61196-9-2 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2020-07-15 |  | 2021-10-12 | 2022-02-28 | Florence Otieno | IEC SC46A Coaxial Cables | 11 | 1
J-STD-038-B | PublAnnouncePosted (100%) | TIA-Only | 100 | This is an update of J-STD-038-A which is a TIA only document and jointly developed with ATIS. This project was created so that the reaffirmation ballot can be sent to the committee. |  | 2020-07-22 | 2021-04-12 | 2021-04-26 | 2021-03-02 | Teesha Jenkins | TR-45 Mobile and Point-to-Point Communications Standards | 6 | 1
568.0-E-1 | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2020-07-31 | 2022-07-25 | 2022-08-16 | 2022-07-21 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 19 | 1
862-C | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2020-07-31 | 2022-06-28 | 2022-08-16 | 2022-06-16 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 13 | 1
IEC 61744 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2020-08-03 |  | 2022-05-03 | 2022-05-03 | Florence Otieno | IEC TC86 Fibre Optics | 11 | 1
IEC 61196-1-200 ED3 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-06-30 | 2020-08-14 |  | 2021-10-04 | 2022-01-24 | Florence Otieno | IEC SC46A Coaxial Cables | 8 | 1
IEC 61755-1 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2020-08-26 |  | 2021-06-21 | 2022-09-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
IEC 60794-2-23 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-03-31 | 2020-09-09 |  | 2021-12-07 | 2022-09-13 | Florence Otieno | IEC SC86A Fibres & Cables | 7 | 1
IEC 63267-1 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-12-31 | 2020-09-09 |  | 2022-09-06 | 2022-09-06 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
IEC 60966-3-4 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-12-31 | 2020-09-09 |  | 2021-10-04 | 2022-05-02 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
IEC 60966-3-3 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-12-31 | 2020-09-09 |  | 2021-10-04 | 2022-05-02 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
IEC 60794-2-24 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-03-31 | 2020-09-10 |  | 2021-06-01 | 2022-09-13 | Florence Otieno | IEC SC86A Fibres & Cables, IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 7 | 1
IEC 61300-3-35 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-09-30 | 2020-09-18 |  | 2021-09-16 | 2022-09-13 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 17 | 1
IEC 61300-1 ED5 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-05-31 | 2020-09-21 |  | 2022-01-31 | 2022-03-21 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
IEC 61300-2-1 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-02-28 | 2020-09-21 |  | 2022-01-05 | 2022-04-04 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 9 | 1
IEC 61300-3-45 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2020-09-30 |  | 2022-02-01 | 2022-05-02 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 7 | 1
IEC 60794-1-404 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-04-30 | 2020-10-01 |  | 2022-01-10 | 2022-02-07 | Florence Otieno | IEC SC86A Fibres & Cables | 10 | 1
IEC 61300-2-5 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-09-30 | 2020-10-01 |  | 2021-09-16 | 2022-09-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 10 | 1
492AAAF-A | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2020-10-07 |  | 2020-11-17 | 2020-11-17 | Teesha Jenkins | TR-42.12 Optical Fibers and Cables | 0 | 1
IEC TR 60825-13 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-03-31 | 2020-10-07 |  | 2022-06-21 | 2022-09-27 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 8 | 1
IEC 61196-1-100 ED3 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-04-30 | 2020-10-12 |  | 2021-08-23 | 2022-01-11 | Florence Otieno | IEC SC46A Coaxial Cables | 8 | 1
IEC 61300-2-18 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2020-10-15 |  | 2021-06-28 | 2022-09-27 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 7 | 1
IEC 61300-3-33 ED3 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-03-31 | 2020-10-15 |  | 2021-12-07 | 2022-01-24 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
606-D | PublAnnouncePosted (100%) | ANSI Project | 100 | This will be published as an ANSI standard. |  | 2020-10-17 | 2021-10-07 | 2022-08-24 | 2022-03-25 | Teesha Jenkins | TR-42.3 Commercial Building Telecommunications Pathways and Spaces | 17 | 1
5048-1 (TIA-Adopted) | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2020-10-17 | 2021-06-11 | 2022-08-16 | 2021-06-11 | Teesha Jenkins | TR-42.3 Commercial Building Telecommunications Pathways and Spaces | 10 | 1
102.BACD-B-3 | PublAnnouncePosted (100%) | TIA-Only | 100 | Addendum 3 to 102.BACD-B |  | 2020-10-19 | 2021-04-14 | 2021-04-26 | 2021-02-23 | Victoria Mitchell | TR-8.19 Wireline System Interfaces | 13 | 1
IEC 61280-4-1/AMD1 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-08-30 | 2020-10-22 |  | 2021-06-22 | 2021-12-07 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 8 | 1
942-B-1 | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2020-10-24 | 2022-02-15 | 2022-08-16 | 2022-03-08 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 25 | 1
IEC 61753-021-02 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-09-30 | 2020-10-26 |  | 2022-08-16 | 2022-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 14 | 1
IEC 61753-021-06 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-09-30 | 2020-10-26 |  | 2022-08-16 | 2022-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 14 | 1
ISO/IEC 14543-5-103 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-12-31 | 2020-10-27 |  | 2021-06-28 | 2022-07-26 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 5 | 1
ISO/IEC 14543-5-104 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-12-31 | 2020-10-27 |  | 2021-06-28 | 2021-08-23 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 5 | 1
IEC TR 62000 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2020-11-01 |  | 2021-06-02 | 2021-07-12 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC 61753-081-02 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2020-11-01 |  | 2022-08-01 | 2022-08-01 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 14 | 1
IEC 61169-21 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-08-30 | 2020-11-05 |  | 2021-11-15 | 2022-02-07 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 6 | 1
IEC 61169-17 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  |  | 2020-11-05 |  | 2021-11-15 | 2022-01-12 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 9 | 1
607-D-1 | PublAnnouncePosted (100%) | ANSI Project | 100 | This project is an addendum to ANSI/TIA-607-D. |  | 2020-11-11 | 2021-07-14 | 2021-10-04 | 2022-03-25 | Cheryl Thibideau | TR-42.3 Commercial Building Telecommunications Pathways and Spaces | 12 | 1
492CAAC-A | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2020-11-11 |  | 2020-11-17 | 2020-11-17 | Teesha Jenkins | TR-42.12 Optical Fibers and Cables | 0 | 1
IEC 61196-11-1 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2020-11-13 |  | 2021-10-12 | 2022-02-28 | Florence Otieno | IEC SC46A Coaxial Cables | 8 | 1
IEC 61196-11 ED2 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-04-30 | 2020-11-13 |  | 2022-01-18 | 2022-02-28 | Florence Otieno | IEC SC46A Coaxial Cables | 10 | 1
IEC 61753-089-02 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-09-30 | 2020-11-17 |  | 2022-06-13 | 2022-08-04 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
IEC 62077 ED4 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-09-30 | 2020-11-17 |  | 2022-06-13 | 2022-08-04 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 10 | 1
IEC 61753-053-02 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-09-30 | 2020-11-17 |  | 2022-06-06 | 2022-07-25 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 13 | 1
IEC 60153-4 ED4 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-07-31 | 2020-11-18 |  | 2022-03-24 | 2022-05-10 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 9 | 1
IEC 61196-4 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2020-11-20 |  | 2021-09-20 | 2022-09-07 | Florence Otieno | IEC SC46A Coaxial Cables | 11 | 1
IEC 61196-4-1 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2020-11-20 |  | 2021-09-20 | 2022-08-29 | Florence Otieno | IEC SC46A Coaxial Cables | 10 | 1
222-I | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2020-11-24 |  | 2020-12-07 | 2020-12-07 | Cheryl Thibideau | TR-14 Structural Stds for Steel Antenna Towers & Antenna Supporting Structure | 2 | 1
222-H-2 | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2020-11-24 |  | 2020-12-07 | 2020-12-07 | Cheryl Thibideau | TR-14 Structural Stds for Steel Antenna Towers & Antenna Supporting Structure | 2 | 1
322-A | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2020-11-24 |  | 2020-12-08 | 2020-12-07 | Cheryl Thibideau | TR-14 Structural Stds for Steel Antenna Towers & Antenna Supporting Structure | 2 | 1
5053-A | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2020-11-24 |  | 2020-12-08 | 2020-12-08 | Cheryl Thibideau | TR-14 Structural Stds for Steel Antenna Towers & Antenna Supporting Structure | 3 | 1
IEC 61196-1-124 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-11-30 | 2020-11-26 |  | 2022-06-13 | 2022-08-04 | Florence Otieno | IEC SC46A Coaxial Cables | 11 | 1
IEC 61196-1-123 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2020-11-26 |  | 2021-09-17 | 2022-07-07 | Florence Otieno | IEC SC46A Coaxial Cables | 10 | 1
IEC 60794-1-310 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-12-31 | 2020-12-01 |  | 2021-10-25 | 2022-02-14 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 61196-1-125 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-10-31 | 2020-12-01 |  | 2022-07-05 | 2022-08-22 | Florence Otieno | IEC SC46A Coaxial Cables | 10 | 1
IEC 62783-1 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-08-31 | 2020-12-03 |  | 2022-05-02 | 2022-05-02 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 6 | 1
IEC 61156-11 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2020-12-03 |  | 2022-03-07 | 2022-03-07 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 5 | 1
IEC 62783-2 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-08-31 | 2020-12-03 |  | 2022-09-19 | 2022-09-19 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 2 | 1
526-28 (TIA Adopted) | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2020-12-16 | 2021-09-14 | 2022-08-24 | 2022-03-25 | Teesha Jenkins | TR-42.11 Optical Systems | 18 | 1
IEC 62037-2 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2020-12-20 |  | 2021-09-13 | 2021-11-01 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 3 | 1
IEC 62037-6 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2020-12-26 |  | 2021-09-13 | 2021-11-01 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 3 | 1
IEC 61196-1-126 ED1 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-10-31 | 2021-01-04 |  | 2022-07-05 | 2022-08-22 | Florence Otieno | IEC SC46A Coaxial Cables | 10 | 1
IEC TR 62285 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-01-31 | 2021-01-05 |  | 2022-04-04 | 2022-04-04 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC TR 63367 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-04-30 | 2021-01-15 |  | 2021-06-14 | 2021-09-08 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 6 | 1
IEC 63267-2-2 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-12-31 | 2021-01-21 |  | 2022-04-04 | 2022-07-06 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 5 | 1
526-7-A (Reaffirmation) | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2021-02-03 | 2022-05-13 | 2022-08-24 | 2022-05-04 | Teesha Jenkins | TR-42.11 Optical Systems | 9 | 1
IEC 61300-3-4 ED4 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-12-31 | 2021-02-04 |  | 2022-09-07 | 2022-09-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 10 | 1
5070 | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2021-02-05 | 2021-02-05 | 2021-02-09 | 2021-02-09 | Cheryl Thibideau | TR-42.7 Telecommunications Copper Cabling Systems | 1 | 1
ISO/IEC 15067-3-30 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-02-05 |  | 2021-11-01 | 2022-07-26 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 8 | 1
455-204-A | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2021-02-12 |  | 2021-02-17 | 2021-03-04 | Cheryl Thibideau | TR-42.12 Optical Fibers and Cables | 5 | 1
455-203-B | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2021-02-12 |  | 2021-02-17 | 2021-03-04 | Cheryl Thibideau | TR-42.12 Optical Fibers and Cables | 6 | 1
455-133-B | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2021-02-12 |  | 2021-03-08 | 2021-03-04 | Cheryl Thibideau | TR-42.12 Optical Fibers and Cables | 5 | 1
ISO/IEC 15045-4-1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2021-02-12 |  | 2022-03-07 | 2022-03-08 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 6 | 1
ISO/IEC 18012-3 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-02-12 |  | 2022-03-21 | 2022-03-21 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 7 | 1
ISO/IEC 15045-4-2 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2021-02-12 |  | 2022-03-07 | 2022-03-08 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 6 | 1
ISO/IEC 15067-3-51 ED1 | Committee (CD-60%) | IEC TAG Project | 60 | The experts requested a small change in the title by deleting the word "Protected" before "On-Premises". The word "Protected" was removed because protection is provided by the gateway, not the Energy Management Agent. Please adjust the title in the SC 25 records. OLD TITLE: Framework of a Protected On-Premises Narrow AI Engine for an Energy Management System using Energy Management Agents NEW TITLE: Framework of an On-Premises Narrow AI Engine for an Energy Management |  | 2021-02-19 |  | 2021-11-08 | 2021-11-08 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 5 | 1
IEC 60794-1-402 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-02-20 |  | 2021-06-01 | 2021-06-21 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC 60793-2-10/AMD1 ED7 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-08-30 | 2021-03-04 |  | 2021-07-15 | 2021-10-12 | Florence Otieno | IEC SC86A Fibres & Cables | 7 | 1
IEC 61300-2-22 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-12-30 | 2021-03-09 |  | 2021-11-15 | 2022-01-24 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 7 | 1
IEC 61300-2-43 ED3 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-10-31 | 2021-03-09 |  | 2022-06-27 | 2022-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 11 | 1
IEC 60793-1-1 ED5 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-01-31 | 2021-04-01 |  | 2022-01-25 | 2022-04-26 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 60793-1-44 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-07-31 | 2021-04-01 |  | 2022-06-13 | 2022-06-13 | Florence Otieno | IEC SC86A Fibres & Cables | 5 | 1
IEC 60794-2-10 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2021-04-01 |  | 2022-01-25 | 2022-06-01 | Florence Otieno | IEC SC86A Fibres & Cables | 7 | 1
102.AACA-B | PublAnnouncePosted (100%) | TIA-Only | 100 | 4/8/21 - General ballot used for motion approval to open project, This is the date used in the "meeting date" field below. 5/3/21 - Project changed from an ANSI to a TIA-only, per Tim Woodward. |  | 2021-04-08 | 2021-09-08 | 2021-10-04 | 2021-08-19 | Teesha Jenkins | TR-8.3 Encryption Subcommittee | 16 | 1
IEC 60794-1-1 ED5 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2021-04-15 |  | 2022-01-25 | 2022-05-23 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 60794-1-301 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-04-30 | 2021-04-15 |  | 2022-03-02 | 2022-03-02 | Florence Otieno | IEC SC86A Fibres & Cables | 5 | 1
IEC 60794-1-305 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-04-30 |  | 2022-01-25 | 2022-09-27 | Florence Otieno | IEC SC86A Fibres & Cables | 5 | 1
IEC 61169-72 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-12-31 | 2021-04-30 |  | 2021-09-13 | 2022-06-13 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 3 | 1
IEC 60794-1-311 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-05-01 |  | 2022-02-28 | 2022-02-28 | Florence Otieno | IEC SC86A Fibres & Cables | 5 | 1
IEC 61300-2-21 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-12-31 | 2021-05-06 |  | 2021-08-23 | 2021-08-23 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 3 | 1
IEC 60794-1-307 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-05-07 |  | 2021-06-01 | 2022-07-07 | Florence Otieno | IEC SC86A Fibres & Cables | 5 | 1
IEC 61754-20/AMD1 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-01-31 | 2021-05-07 |  | 2021-11-30 | 2022-05-10 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 8 | 1
IEC 60794-1-312 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-05-13 |  | 2022-02-28 | 2022-02-28 | Florence Otieno | IEC SC86A Fibres & Cables | 3 | 1
IEC 61280-1-4 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-10-31 | 2021-05-13 |  | 2022-07-26 | 2022-07-26 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 6 | 1
IEC 61726 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-12-30 | 2021-05-18 |  | 2021-12-13 | 2022-03-21 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
IEC 62149-4 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-02-28 | 2021-05-25 |  | 2021-09-27 | 2021-12-07 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 4 | 1
PNW JTC1-SC25-3035 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  | 2025-09-30 | 2021-05-28 |  | 2021-06-18 | 2021-06-18 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 2 | 1
ISO/IEC 14543-4-302 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-05-28 |  | 2021-11-30 | 2022-08-01 | Florence Otieno | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 7 | 1
ISO/IEC 10192-4-2 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2021-06-01 |  | 2021-06-23 | 2021-06-23 | Teesha Jenkins | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 3 | 1
IEC 61156-7 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2024-10-31 | 2021-06-01 |  | 2022-07-11 | 2022-07-11 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 7 | 1
IEC 61156-8 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-06-01 |  | 2022-07-11 | 2022-07-11 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 7 | 1
PNW 86A-2124 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  | 2024-06-30 | 2021-06-02 |  | 2021-06-07 | 2021-06-08 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC 60794-7 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2021-06-02 |  | 2022-05-16 | 2022-05-17 | Florence Otieno | IEC SC86A Fibres & Cables | 1 | 1
IEC 60794-1-309 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2021-06-04 |  | 2022-01-25 | 2022-01-25 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 61300-3-27 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-04-30 | 2021-06-04 |  | 2021-06-07 | 2021-06-09 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 10 | 1
1179-B | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2021-06-15 |  | 2022-07-11 | 2022-07-11 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 8 | 1
5017-A | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2021-06-15 |  | 2022-08-29 | 2022-08-29 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 7 | 1
5046 (WITHDRAWN) | Project Cancelled | TIA-Only | 100 |  |  | 2021-06-15 | 2021-06-15 | 2022-08-24 | 2021-07-01 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 0 | 1
4994(WITHDRAWN) | Project Cancelled | ANSI Project | 100 | Withdraw standard |  | 2021-06-15 | 2021-06-15 | 2022-08-18 | 2021-07-01 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 0 | 1
942-C | Committee Ballot (30%) | ANSI Project | 30 |  |  | 2021-06-17 |  | 2022-01-28 | 2022-07-21 | Teesha Jenkins | TR-42.1 Premises Telecommunications Infrastructure | 11 | 1
ISO/IEC 18012-4 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-06-21 |  | 2022-03-21 | 2022-03-21 | Teesha Jenkins | USNC TAG SC 25/WG 1 to ISO/IEC JTC1/SC25/WG1 Home Electronic System | 5 | 1
IEC 61290-1 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 60 |  | 2023-01-31 | 2021-06-23 |  | 2021-12-02 | 2022-02-28 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 7 | 1
IEC TR 61292-1 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2022-10-31 | 2021-06-23 |  | 2022-01-13 | 2022-02-28 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 8 | 1
IEC 61935-4 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-05-31 | 2021-06-29 |  | 2022-03-07 | 2022-06-01 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 5 | 1
IEC 62148-22 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2021-07-01 |  | 2022-07-11 | 2022-07-11 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 8 | 1
IEC 61196-10-1 ED2 | Approval (FDIC-90%) | IEC TAG Project | 90 |  | 2022-12-31 | 2021-07-02 |  | 2022-09-12 | 2022-09-12 | Florence Otieno | IEC SC46A Coaxial Cables | 9 | 1
IEC 61196-10 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-07-02 |  | 2022-01-24 | 2022-09-12 | Florence Otieno | IEC SC46A Coaxial Cables | 9 | 1
IEC 61196-5 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2022-12-31 | 2021-07-02 |  | 2022-02-09 | 2022-05-10 | Florence Otieno | IEC SC46A Coaxial Cables | 7 | 1
IEC 61196-1-119 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-07-02 |  | 2022-08-01 | 2022-08-01 | Florence Otieno | IEC SC46A Coaxial Cables | 10 | 1
IEC TR 61282-16 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-07-07 |  | 2021-07-12 | 2022-02-28 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 6 | 1
PNW 86C-1734 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  | 2023-06-30 | 2021-07-08 |  | 2021-07-12 | 2021-07-15 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 2 | 1
IEC 62149-12 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2021-07-08 |  | 2022-07-26 | 2022-07-26 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 8 | 1
IEC TR 61292-12 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2021-07-09 |  | 2022-06-07 | 2022-08-29 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 6 | 1
IEC 61300-2-34 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-10-31 | 2021-07-15 |  | 2022-09-06 | 2022-09-06 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 6 | 1
PNW TS 86b-4507 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2021-08-10 |  | 2021-08-16 | 2021-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 2 | 1
10-A | Proj Form Initiated (20%) | ANSI Project | 20 |  | 2022-06-30 | 2021-08-10 |  | 2021-09-21 | 2021-09-21 | Teesha Jenkins | TR-45 Mobile and Point-to-Point Communications Standards, TR-45 Working Group on Microwave Systems | 2 | 1
SB Cybersecurity Whitepaper Fall 2021 | Proj Form Initiated (20%) | TIA-Only | 0 | Develop whitepaper to guide further development of the SB Cybersecurity Assessment Criteria. -- Base document: Cyber AC V1.5 -- In support of deliverable: Cyber AC V2.0; SB Handbook | 2021-11-30 | 2021-08-11 |  | 2021-09-15 | 2021-09-21 | Marta Soncodi | Smart Buildings Cybersecurity | 1 | 1
IEC 61300-2-11 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-06-30 | 2021-08-27 |  | 2021-08-30 | 2021-12-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 4 | 1
PNW 86B-4523 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2021-09-03 |  | 2021-09-07 | 2021-09-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 2 | 1
IEC 61300-2-33 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-12-30 | 2021-09-15 |  | 2021-09-20 | 2022-01-10 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 4 | 1
88.2-F-1 | PublAnnouncePosted (100%) | TIA-Only | 100 | Project created to allow for ballot to be linked. Missing information will be completed once (online) motion ballot completed to begin project. |  | 2021-10-05 | 2022-05-19 | 2022-08-16 | 2022-05-05 | Victoria Mitchell | TR-8.18 Wireless Systems Compatibility - Interference and Coverage | 11 | 1
455-111-B | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2021-10-06 |  | 2022-04-15 | 2022-04-15 | Teesha Jenkins | TR-42.12 Optical Fibers and Cables | 7 | 1
184-A-2 | Committee Ballot (40%) | TIA-Only | 40 |  |  | 2021-10-12 |  | 2022-06-28 | 2022-06-28 | Teesha Jenkins | TR-42.7 Telecommunications Copper Cabling Systems | 5 | 1
IEC 60966-4 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2021-10-19 |  | 2022-06-07 | 2022-09-20 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
IEC 60966-4-1 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2021-10-19 |  | 2022-06-07 | 2022-09-20 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
IEC 60966-3 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2021-10-19 |  | 2022-06-07 | 2022-09-20 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
IEC 60966-3-1 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2021-10-19 |  | 2022-06-07 | 2022-09-20 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 7 | 1
IEC 60966-2-1 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-10-19 |  | 2022-06-07 | 2022-09-20 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 8 | 1
IEC 60966-2-2 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-06-30 | 2021-10-20 |  | 2022-06-07 | 2022-09-20 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 8 | 1
IEC 61754-7-5 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-06-30 | 2021-10-27 |  | 2022-06-07 | 2022-09-07 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 6 | 1
IEC 61300-2-26 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-06-30 | 2021-11-09 |  | 2021-11-15 | 2022-05-18 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 5 | 1
IEC 60794-1-303 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-07-31 | 2021-11-17 |  | 2022-06-13 | 2022-06-13 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 60794-1-212 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-11-30 | 2021-11-18 |  | 2022-06-02 | 2022-06-02 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 60794-2-50 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-11-18 |  | 2022-06-13 | 2022-06-13 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 61196-8 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-11-24 |  | 2022-04-04 | 2022-08-08 | Florence Otieno | IEC SC46A Coaxial Cables | 5 | 1
IEC 61196-8-1 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-12-31 | 2021-11-25 |  | 2021-11-29 | 2022-08-08 | Florence Otieno | IEC SC46A Coaxial Cables | 4 | 1
IEC 61196-9-1 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-12-31 | 2021-11-25 |  | 2021-11-29 | 2022-08-08 | Florence Otieno | IEC SC46A Coaxial Cables | 3 | 1
IEC 61196-9 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-11-25 |  | 2022-04-05 | 2022-08-08 | Florence Otieno | IEC SC46A Coaxial Cables | 6 | 1
IEC 62007-1/AMD1 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-05-31 | 2021-11-29 |  | 2022-04-25 | 2022-07-25 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 7 | 1
IEC TR 61292-4 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2021-11-29 |  | 2022-08-30 | 2022-08-30 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 6 | 1
IEC TR 61292-9 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2021-11-29 |  | 2022-08-29 | 2022-08-29 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 7 | 1
IEC 62148-12/AMD1 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-05-31 | 2021-11-29 |  | 2022-04-25 | 2022-04-25 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 5 | 1
IEC 60794-1-306 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-11-30 |  | 2021-12-14 | 2022-07-18 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 60794-1-217 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2021-12-01 |  | 2022-06-02 | 2022-06-02 | Florence Otieno | IEC SC86A Fibres & Cables | 7 | 1
88.1-F | PublAnnouncePosted (100%) | TIA-Only | 100 |  |  | 2021-12-02 | 2022-04-29 | 2022-05-02 | 2022-04-26 | Victoria Mitchell | TR-8.18 Wireless Systems Compatibility - Interference and Coverage | 15 | 1
IEC 61291-2 ED5 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-09-30 | 2021-12-02 |  | 2022-07-07 | 2022-07-07 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 6 | 1
IEC TR 61292-6 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2023-06-30 | 2021-12-02 |  | 2022-08-30 | 2022-08-30 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 6 | 1
IEC 61169-10 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-12-03 |  | 2022-01-12 | 2022-03-28 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 6 | 1
IEC 60974-1-217 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2021-12-03 |  | 2021-12-06 | 2021-12-20 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC 61169-70 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-12-03 |  | 2021-12-06 | 2022-03-21 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 5 | 1
IEC 63138-2 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2021-12-07 |  | 2021-12-13 | 2022-04-04 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 5 | 1
IEC 62343 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-09-30 | 2021-12-08 |  | 2022-07-11 | 2022-07-11 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 6 | 1
IEC 60794-1-308 ED1 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-07-31 | 2021-12-08 |  | 2022-07-18 | 2022-07-18 | Florence Otieno | IEC SC86A Fibres & Cables | 8 | 1
IEC TR 62343-6-12 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2021-12-08 |  | 2021-12-13 | 2022-08-29 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 5 | 1
IEC 61169-64 ED2 | Proposal (NP-20%) | IEC TAG Project | 20 |  |  | 2021-12-14 |  | 2022-01-10 | 2022-01-11 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 1 | 1
IEC TR 62627-01 ED3 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-03-31 | 2021-12-15 |  | 2022-06-07 | 2022-08-08 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 8 | 1
IEC 60794-2-22 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2023-12-31 | 2021-12-17 |  | 2022-06-13 | 2022-06-13 | Florence Otieno | IEC SC86A Fibres & Cables | 13 | 1
IEC 61300-2-38 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-06-30 | 2021-12-17 |  | 2022-01-10 | 2022-08-29 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 5 | 1
IEC 60601-2-57 ED2 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  |  | 2021-12-23 |  | 2022-06-27 | 2022-06-27 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 6 | 1
ISO 11553-2 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-12-31 | 2022-01-21 |  | 2022-01-25 | 2022-01-25 | Florence Otieno | IEC TC76 Optical Radiation Safety & Laser Equipment | 1 | 1
569-E-1 | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2022-01-25 | 2022-06-28 | 2022-08-16 | 2022-06-16 | Teesha Jenkins | TR-42.3 Commercial Building Telecommunications Pathways and Spaces | 9 | 1
568.5-1 | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2022-01-26 |  | 2022-06-17 | 2022-06-17 | Teesha Jenkins | TR-42.7 Telecommunications Copper Cabling Systems | 2 | 1
568.4-E | PublAnnouncePosted (100%) | ANSI Project | 100 |  |  | 2022-01-26 | 2022-07-12 | 2022-08-16 | 2022-07-07 | Teesha Jenkins | TR-42.7 Telecommunications Copper Cabling Systems | 10 | 1
1183-B | Re-Ballot_Default (60%) | ANSI Project | 60 |  |  | 2022-01-26 |  | 2022-06-30 | 2022-06-30 | Teesha Jenkins | TR-42.7 Telecommunications Copper Cabling Systems | 4 | 1
622.4 | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2022-01-26 |  | 2022-05-09 | 2022-05-09 | Teesha Jenkins | TR-42.13 Passive Optical Devices and Fiber Optic Metrology | 9 | 1
622.5 | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2022-01-26 |  | 2022-05-09 | 2022-05-09 | Teesha Jenkins | TR-42.13 Passive Optical Devices and Fiber Optic Metrology | 9 | 1
Assessment Criteria v2.0 | Abstract | Technology Project | 20 |  | 2022-06-30 | 2022-01-31 |  | 2022-01-31 | 2022-01-10 | Marta Soncodi | Smart Building Steering Committee, Smart Buildings Cybersecurity, Smart Buildings Infrastructure & Management, Smart Buildings Occupant Services and Experience | 0 | 1
IEC TR 63431 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2022-02-07 |  | 2022-02-14 | 2022-02-14 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC 61196-13 | Proposal (NP-20%) | IEC TAG Project | 20 |  | 2024-07-31 | 2022-02-11 |  | 2022-02-22 | 2022-02-22 | Florence Otieno | IEC SC46A Coaxial Cables | 2 | 1
IEC 61196-13 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-07-31 | 2022-02-11 |  | 2022-08-08 | 2022-08-09 | Florence Otieno | IEC SC46A Coaxial Cables | 4 | 1
IEC 61300-2-27 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-12-31 | 2022-02-18 |  | 2022-03-02 | 2022-06-01 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 4 | 1
IEC 61300-2-44 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-12-31 | 2022-02-18 |  | 2022-03-03 | 2022-06-01 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 4 | 1
IEC 63466 ED1 | Preparatory (WD-40%) | IEC TAG Project | 40 |  | 2024-06-30 | 2022-03-15 |  | 2022-08-08 | 2022-08-08 | Florence Otieno | IEC TC46 Cables, Wires, Waveguides, R.F. Connectors, R.F. and Microwave Passive Components and Accessories | 3 | 1
IEC 61196-1-127 ED1 | Preparatory (WD-40%) | IEC TAG Project | 40 |  | 2024-10-31 | 2022-03-15 |  | 2022-08-08 | 2022-08-08 | Florence Otieno | IEC SC46A Coaxial Cables | 3 | 1
IEC 61196-13-1 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2022-03-23 |  | 2022-08-08 | 2022-08-08 | Florence Otieno | IEC SC46A Coaxial Cables | 4 | 1
IEC TR 63442 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2022-04-12 |  | 2022-04-19 | 2022-04-19 | Florence Otieno | IEC SC86A Fibres & Cables | 2 | 1
IEC 60794-2-20 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-06-30 | 2022-04-12 |  | 2022-04-25 | 2022-09-07 | Florence Otieno | IEC SC86A Fibres & Cables | 6 | 1
IEC 62522 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-12-31 | 2022-04-14 |  | 2022-04-25 | 2022-08-04 | Florence Otieno | IEC TC86 Fibre Optics | 4 | 1
IEC 62149-3 ED4 | Enquiry (CDV-80%) | IEC TAG Project | 80 |  | 2024-04-30 | 2022-04-28 |  | 2022-07-07 | 2022-08-16 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 9 | 1
IEC TS 61156-1-2 ED1 | Preparatory (WD-40%) | IEC TAG Project | 40 |  | 2025-10-31 | 2022-05-02 |  | 2022-09-08 | 2022-09-08 | Florence Otieno | IEC SC46C Wires & Symmetric Cables | 3 | 1
IEC 60875-1 ED7 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2025-06-30 | 2022-05-06 |  | 2022-05-17 | 2022-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 4 | 1
IEC 61753-082-02 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2025-06-30 | 2022-05-10 |  | 2022-05-17 | 2022-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 2 | 1
IEC 61300-3-46 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2025-06-30 | 2022-05-10 |  | 2022-05-17 | 2022-08-16 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 3 | 1
IEC 61300-3-3 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2025-06-30 | 2022-05-13 |  | 2022-05-24 | 2022-08-29 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 4 | 1
IEC 60793-1-41 ED4 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-01-31 | 2022-05-17 |  | 2022-06-06 | 2022-06-06 | Florence Otieno | IEC SC86A Fibres & Cables | 3 | 1
IEC 60793-1-45 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-01-31 | 2022-05-17 |  | 2022-06-06 | 2022-09-27 | Florence Otieno | IEC SC86A Fibres & Cables | 4 | 1
5048 (Reaffirmation) | Formal Ballot (40%) | ANSI Project | 40 |  |  | 2022-06-06 |  | 2022-08-24 | 2022-08-03 | Teesha Jenkins | TR-42.3 Commercial Building Telecommunications Pathways and Spaces | 8 | 1
IEC 61280-4-2 ED3 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-08-31 | 2022-06-29 |  | 2022-07-26 | 2022-07-26 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 3 | 1
TBD <PNW TS SYCSMARTCITIES-259 ED1> | Proposal (NP-20%) | IEC TAG Project | 20 |  | 2024-06-30 | 2022-07-01 |  | 2022-07-07 | 2022-07-07 | Florence Otieno | US TAG to IEC Systems Committee on Smart Cities-Electrotechnical Aspects | 2 | 1
IEC 60974-1-111 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2022-07-11 |  | 2022-07-18 | 2022-07-18 | Florence Otieno | IEC SC86A Fibres & Cables | 3 | 1
IEC 62148-17 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2022-07-12 |  | 2022-07-26 | 2022-07-26 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 3 | 1
102.CAAB-E-1 | Committee Ballot (40%) | TIA-Only | 40 |  | 2022-11-30 | 2022-07-12 |  | 2022-08-30 | 2022-08-30 | Teesha Jenkins | TR-8.1 Equipment Measurement Procedures | 6 | 1
102.AABD-B-1 | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2022-07-12 |  | 2022-08-04 | 2022-08-02 | Teesha Jenkins | TR-8.10 Trunking and Conventional Control | 1 | 1
102.AABF-D-1 | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2022-07-12 |  | 2022-08-04 | 2022-08-02 | Teesha Jenkins | TR-8.10 Trunking and Conventional Control | 1 | 1
IEC 60793-2-50 ED7 | Committee (CD-60%) | IEC TAG Project | 60 |  |  | 2022-07-13 |  | 2022-07-26 | 2022-07-26 | Florence Otieno | IEC SC86A Fibres & Cables | 3 | 1
5077.1 | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2022-07-14 |  | 2022-08-04 | 2022-08-04 | Teesha Jenkins | TR-60.B Information Management | 1 | 1
PNW 86C-1815 ED1 | Preliminary (PWI-10%) | IEC TAG Project | 10 |  |  | 2022-07-22 |  | 2022-07-25 | 2022-07-26 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 2 | 1
PNW 86C-1814 ED1 | Preliminary (PWI-10%) | IEC TAG Project | 10 |  |  | 2022-07-22 |  | 2022-07-25 | 2022-07-26 | Florence Otieno | IEC SC86C Fibre Optics Systems & Active Devices | 2 | 1
IEC 60153-2 ED4 | Preliminary (PWI-10%) | IEC TAG Project | 10 |  |  | 2022-07-28 |  | 2022-08-01 | 2022-08-04 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 1 | 1
IEC 63185 ED2 | Preliminary (PWI-10%) | IEC TAG Project | 10 |  |  | 2022-07-28 |  | 2022-08-01 | 2022-08-04 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 1 | 1
102.AABF-D-2 | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2022-08-02 |  | 2022-08-04 | 2022-08-02 | Teesha Jenkins | TR-8.10 Trunking and Conventional Control | 1 | 1
102.AABD-B-2 | Proj Form Initiated (20%) | TIA-Only | 20 |  |  | 2022-08-02 |  | 2022-08-04 | 2022-08-02 | Teesha Jenkins | TR-8.10 Trunking and Conventional Control | 1 | 1
PNW 46F-628 ED1 | Proposal (NP-20%) | IEC TAG Project | 20 | IEC standard number TBD | 2024-08-31 | 2022-08-15 |  | 2022-08-22 | 2022-08-22 | Florence Otieno | IEC SC46F R.F. & Microwave Passive Components | 2 | 1
IEC 60974-1-201 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-12-31 | 2022-08-24 |  | 2022-08-29 | 2022-08-29 | Florence Otieno | IEC SC86A Fibres & Cables | 3 | 1
IEC 60793-1-22 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-06-30 | 2022-08-24 |  | 2022-08-29 | 2022-09-07 | Florence Otieno | IEC SC86A Fibres & Cables | 3 | 1
329.3-A | Proj Form Initiated (20%) | TIA-Only | 20 |  | 2023-09-30 | 2022-08-26 |  | 2022-08-30 | 2022-08-30 | Teesha Jenkins | TR-8.11 Antenna Systems | 2 | 1
IEC 60974-1-209 ED1 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2024-12-31 | 2022-08-30 |  | 2022-09-06 | 2022-09-07 | Florence Otieno | IEC SC86A Fibres & Cables | 3 | 1
IEC 62005-9-1 ED2 | Committee (CD-60%) | IEC TAG Project | 60 |  | 2025-04-30 | 2022-09-09 |  | 2022-09-19 | 2022-09-19 | Florence Otieno | IEC SC86B Fibre Optic Interconnecting Devices & Passive Components | 3 | 1
568.3-E-1 | Proj Form Initiated (20%) | ANSI Project | 20 |  |  | 2022-09-15 |  | 2022-09-15 | 2022-09-15 | Teesha Jenkins | TR-42.11 Optical Systems | 0 | 1